    Project Planning Phase
 Milestone and Activity List
Date
14 November 2022
Team ID
  PNT2022TMID34642
Project Name
  News tracker application
TITLE
DESCRIPTION
DATE
Literature Survey &
10 OCTOBER 2022
 Literature survey on the
Information Gathering
selected project &
 gathering information by
 referring the, technical
papers, research
 publications etc.
Prepare Empathy Map
Prepare Empathy Map
16 OCTOBER 2022
Canvas to capture the user
Pains & Gains, Prepare list of
problem statements
Ideation
List the by organizing the
16 OCTOBER 2022
brainstorming session and
prioritize the top 3 ideas
based on the feasibility &
importance.
Proposed Solution
Prepare the proposed solution
16 OCTOBER 2022
document, which includes the
novelty, feasibility of idea,
business model, social impact,
scalability of solution, etc.
Prepare problem - solution fit
2 NOVEMBER 2022
Problem Solution Fit
document.
30 OCTOBER 2022
Prepare solution architecture
Solution Architecture
document.

---
Customer Journey
Prepare the customer journey
13 NOVEMBER 2022
maps to understand the user
interactions & experiences with
the application (entry to exit).
Prepare the functional
1 NOVEMBER 2022
Functional Requirement
requirement document.
Data Flow Diagrams
Draw the data flow
1 NOVEMBER 2022
diagrams and submit for
review.
1 NOVEMBER 2022
Prepare the technology
Technology Architecture
architecture diagram.
15 NOVEMBER 2022
Prepare the milestones &
Prepare Milestone &
activity list of the project.
Activity List
Develop & submit the
IN PROGRESS
Project Development -
developed code by testing it.
Delivery of Sprint-1, 2, 3 & 4